## Project Planner
Migration Timeline
[7 empty] | Period Highlight: |  | 59 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PHASE | ACTIVITY | ACTIVITY DESCRIPTION | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192
GCDOCS Deployment |  | Timeline not shown here
Migration | Assess | Source Systems |  | 1 | 10
|  | Target System |  | 11 | 5 |  |  | 0%
|  | Data clean-up needs |  | 16 | 15 |  |  | 0%
|  | Business Reqirements (User interviews, IM and RM team reviews) | - User interviews - IM team reviews - RM team reviews | 16 | 10 |  |  | 0%
|  | External pressures and timelines | - Management interviews - Support/maintainance contract reviews - Hardware/software upgrade reviews | 26 | 5 |  |  | 0%
|  | Analyze migration tools |  | 16 | 15 |  |  | 0%
| Plan | Procure resources, hardware and software |  | 31 | 10 |  |  | 0%
|  | Procure migration tool |  | 31 | 10 |  |  | 0%
|  | Assemble migraiton team |  | 16 | 20 |  |  | 0%
|  | Mapping and template definition |  | 41 | 15 |  |  | 0%
|  | Migration document | - Define Content to be Migrated - Processing Plan and Flow - Mapping Details - Location - Meta-data - Versions - Permissions - History - Etc. (account for all Content to be Migrated) - Exclusion of Objects Not to Migrate - File types - Zero Byte Files - Outdated Files - Assumptions - Required Scripts and Customizations - Velocity Scripts - RDIMS Customizations - GCDOCS Customizations - Testing and Results Planning | 48 | 15 |  |  | 0%
| Train | Migration software training |  | 59 | 2 |  |  | 0%
| Deploy | Make necessary RDIMS and GCDOCS changes |  | 55 | 10 |  |  | 0%
|  | Install and configure migraiton software |  | 63 | 25
| Execute | Test migraitons and validation |  | 73 | 10 |  |  | 0%
|  | Production migration | Run tests in earlier phases to calculate processing time. | 83 | 60
|  | Migraiton validation |  | 143 | 5
|  | Migraiton clean-up and error reprocessing |  | 148 | 5
|  | Post process runs | - Link conversion - Custom clean-up - Etc. | 153 | 10
|  | Final delta runs |  | 163 | 2
|  | Results reporting |  | 165 | 10
| Rollout | User training |  | 165 | 20 |  |  | 0%
|  | User client changes |  | 165 | 10 |  |  | 0%
|  | Cutover support |  | 177 | 10